## Summary
DealForge - MVP Tracker (BRD Phase 1)
Source: docs/DealForge_Phase1_BRD Draft.xlsx (88 requirements) ¦ Baseline: main @ 064caee ¦ Date: 26 Sep 2026
Status is evidence-based on code in server/ and src/. Counts are live formulas over Requirements and Backlog.
Requirements by status
Status | Count | % of all
Built | 79 | 89.77%
Partial | 2 | 2.273%
Gap | 0 | 0%
Deferred | 5 | 5.682%
Process | 2 | 2.273%
Total | 88 | 100%
Requirements by priority
Priority | Total | Built | Partial | Gap | Deferred
Must | 65 | 59 | 1 | 0 | 3
Should | 20 | 19 | 1 | 0 | 0
Could | 3 | 1 | 0 | 0 | 2
Total | 88 | 79 | 2 | 0 | 5
Backlog by workstream
Workstream | TODOs | Must | Should | Could | Effort (d, est)
W1 Intake | 10 | 8 | 1 | 1 | 46
W2 Financials | 10 | 9 | 1 | 0 | 48
W3 Screening | 13 | 8 | 5 | 0 | 72
W4 Entity | 4 | 4 | 0 | 0 | 17
W5 Documents | 5 | 2 | 3 | 0 | 27
W6 Governance | 7 | 6 | 1 | 0 | 23
W7 Reporting | 5 | 2 | 3 | 0 | 31
W8 Platform | 6 | 3 | 3 | 0 | 34
W9 NFR/Release | 8 | 5 | 3 | 0 | 25
Total | 68 | 47 | 20 | 1 | 323
Slices
S0 | W0 | Reconcile & freeze
S1 | W1-W3 | Intake governance
S2 | W3-W6 | Financials & returns
S3 | W5-W8 | Screening & scorecard
S4 | W6-W8 | Entity, docs & templates
S5 | W8-W10 | Governance & audit hardening
S6 | W9-W11 | Reporting & output
S7 | W10-W12 | Platform, auth & config
S8 | W12-W13 | Hardening & NFR
S9 | W13-W14 | UAT & sign-off
S10 | W14-W15 | Pilot rollout
Backlog by status
Status | Count | % of backlog
Not started | 0 | 0%
In progress | 0 | 0%
Blocked | 3 | 4.225%
Done | 68 | 95.77%
Deferred | 0 | 0%
Total | 71

## Requirements
Req ID | Module | Requirement | Priority | Phase | Status | Workstream | Mapped TODO | Evidence / Gap
PLT-01 | Platform & Access | Multi-organisation hierarchy | Must | Phase 1 | Built | Platform |  | server/org.js, orgApi.js, GroupStructure.jsx; tests m1
PLT-02 | Platform & Access | Entity-based data isolation | Must | Phase 1 | Built | Platform |  | server/abac.js (CROSS_ORG_READ_ROLES, canRead); m1/m5
PLT-03 | Platform & Access | Role-based access control | Must | Phase 1 | Built | Platform |  | server/rbac.js (14 roles, ACTION_ROLES)
PLT-04 | Platform & Access | Single sign-on + MFA | Must | Phase 1 | Built | W8 Platform | W8-01 | SSO (OIDC/SAML) + MFA; local accounts for externals. See Backlog W8-01. Evidence: docs/evidence/W8-01/
PLT-05 | Platform & Access | User administration | Must | Phase 1 | Built | W8 Platform | W8-06 | User administration hardening: deactivation is immediate (inactive/banned accounts resolve to no actor and lose their live sessions) and every lifecycle action is named and audited (server/config/userAdmin.js + server/users.js + server/admin.js + SuperAdmin.jsx). Evidence: docs/evidence/W8-06/
PLT-06 | Platform & Access | Bilingual-ready interface | Should | Phase 1 | Built | W8 Platform | W8-02 | i18n completion: all core UI strings externalised; RTL demonstrated on Dashboard. See Backlog W8-02. Evidence: docs/evidence/W8-02/
ENT-01 | Entity & Strategy Library | Entity strategy profile | Must | Phase 1 | Built | W4 Entity | W4-03 | server/strategy.js screening_record profile version; docs/evidence/W4-03/
ENT-02 | Entity & Strategy Library | Strategy document upload | Must | Phase 1 | Built | W4 Entity | W4-02 | server/strategy.js indexing + citation; docs/evidence/W4-02/
ENT-03 | Entity & Strategy Library | Sirius group mandate | Must | Phase 1 | Built | W4 Entity | W4-04 | server/config/siriusMandate.js + server/mandate.js (versioned group mandate); docs/evidence/W4-04/
ENT-04 | Entity & Strategy Library | Portfolio register | Must | Phase 1 | Built | W4 Entity | W4-01 | docs/evidence/W4-01/
INT-01 | Opportunity Intake | Single controlled intake channel | Must | Phase 1 | Built | W1 Intake |  | SubmitOpportunity.jsx, pipeline.js
INT-02 | Opportunity Intake | Self-screen before drafting | Must | Phase 1 | Built | W1 Intake | W1-01 | server/config/selfScreen.js six-question screen + evaluateSelfScreen; gate.js POST /api/gate/self-screen and submit 422 block; SubmitOpportunity.jsx pre-form step with stop messages; selfscreen.test.js (12 pass). Evidence: docs/evidence/W1-01/
INT-03 | Opportunity Intake | Below-floor exception route | Must | Phase 1 | Built | W1 Intake | W1-02 | server/config/belowFloor.js evaluateBelowFloor (synergy + IRR>=35% + Sirius escalation) folded into selfScreen.js and gate.js; submit 422 block, below-floor tag persisted and escalated (notify deliver:false), pipeline_transition comment; SubmitOpportunity.jsx route alerts; belowFloor.test.js (6 pass), m2.test.js W1-02 (3 pass). Evidence: docs/evidence/W1-02/
INT-04 | Opportunity Intake | Opportunity type classification | Must | Phase 1 | Built | W1 Intake |  | opportunity_type in OPPORTUNITY_FIELDS (gate.js)
INT-05 | Opportunity Intake | Sourcing channel | Must | Phase 1 | Built | W1 Intake | W1-08 | server/config/sourcingChannel.js side-effects (mandatory channel; IHC/affiliate auto related-party flag; banker/advisor compressed-timeline indicator); gate.js sourcing_channel in evaluateGate + /fields + submit 422 block and persistence; siriusMemo sourcing key fact + side-effects note; SubmitOpportunity.jsx alerts; sourcingChannel.test.js (8 pass), m2.test.js W1-08 (5 pass); evidence docs/evidence/W1-08
INT-06 | Opportunity Intake | Structured Opportunity Overview form (6 sections) | Must | Phase 1 | Built | W1 Intake | W1-03 | server/config/intakeConfig.js six-section model; gate.js GET /api/gate/fields; SubmitOpportunity.jsx renders model; intake.test.js
INT-07 | Opportunity Intake | Accretion Statement | Must | Phase 1 | Built | W1 Intake | W1-04 | accretion fields in intakeConfig.js; rendered in memo (siriusMemoDocx.js); intake.test.js
INT-08 | Opportunity Intake | Qualifying gates checklist (10 gates) | Must | Phase 1 | Built | W1 Intake | W1-05 | 10-gate checklist in server/config/qualifyingGates.js; blocking 422 on any No in server/gate.js submit route; SubmitOpportunity.jsx qualifying-gates card; qualifyingGates.test.js; evidence docs/evidence/W1-05
INT-09 | Opportunity Intake | CEO and CFO attestation | Must | Phase 1 | Built | W1 Intake | W1-06 | server/config/attestations.js (ceo/cfo + subsidiary role specs, configurable attestation_text setting); gate.js loadAttestationTexts/evaluateGate attestations + POST /opportunities/:id/attestations/:key + submit 422 block (attestation_recorded / submit_blocked audits); SubmitOpportunity.jsx attestation card; attestations.test.js (8 pass), m2.test.js W1-06 (4 pass); evidence docs/evidence/W1-06
INT-10 | Opportunity Intake | Greenfield extra tests | Must | Phase 1 | Built | W1 Intake | W1-07 | server/config/greenfield.js extra tests (stage Concept/Feasibility/Initiate, quantified benefit, thesis, budget, secured funding source; Concept capped at a 2-page note); gate.js greenfield in evaluateGate (Concept waives the full pack) + submit 422 block (greenfield_stops audit); SubmitOpportunity.jsx alerts; greenfield.test.js (9 pass), m2.test.js W1-07 (4 pass); evidence docs/evidence/W1-07
INT-11 | Opportunity Intake | Related-party disclosure | Must | Phase 1 | Built | W1 Intake |  | relatedParty.js flag + independent reviewer routing
INT-12 | Opportunity Intake | Duplicate detection | Could | Phase 1 | Built | W1 Intake | W1-10 | duplicates.js + config/duplicates.js cross-group match warning with link/dismiss decisions in duplicate_review, Investment-Team-only (403 for the preparer, subsidiary isolation preserved); duplicates.test.js (8 pass), m3.test.js W1-10 (3 pass); evidence docs/evidence/W1-10
INT-13 | Opportunity Intake | Withdraw submission | Should | Phase 1 | Built | W1 Intake | W1-09 | pipeline.js withdrawn state + reason-required withdraw transition retained in pipeline_transition history and on the opportunity (withdrawn_reason/withdrawn_at); board Withdrawn column; m3.test.js W1-09 (4 pass); evidence docs/evidence/W1-09
DOC-01 | Documents & Completeness | Document checklist by type/stage/flags | Must | Phase 1 | Built | W5 Documents | W5-01 | docs/evidence/W5-01/
DOC-02 | Documents & Completeness | Document upload and storage | Must | Phase 1 | Built | W5 Documents | W5-02 | docs/evidence/W5-02/
DOC-03 | Documents & Completeness | Mandatory-document gate | Must | Phase 1 | Built | W5 Documents |  | evaluateGate, SUBMITTABLE_STATES; tests m2
DOC-04 | Documents & Completeness | Content sufficiency check | Should | Phase 1 | Built | W5 Documents | W5-03 | docs/evidence/W5-03/
DOC-05 | Documents & Completeness | Data-point to source mapping | Should | Phase 1 | Built | W5 Documents | W5-04 | docs/evidence/W5-04/
DOC-06 | Documents & Completeness | Document templates | Should | Phase 1 | Built | W5 Documents | W5-05 | docs/evidence/W5-05/
FIN-01 | Financials & Returns | Financial summary capture (FY-3 to Y+5) | Must | Phase 1 | Built | W2 Financials | W2-01 | server/config/financials.js 8-row x 8-period Part B p.4 matrix with derived growth %/EBITDA margin %/FCF/net debt-EBITDA; SubmitOpportunity.jsx editable grid; siriusMemo.js + SiriusMemoDialog finTable; new-venture actuals optional. Evidence: docs/evidence/W2-01/
FIN-02 | Financials & Returns | Three-statement model upload and check | Must | Phase 1 | Built | W2 Financials | W2-02 | server/config/statementModel.js parses the linked three-statement model (CSV/TSV/JSON, dependency-free) and checks presence of P&L + balance sheet + cash flow and the per-period balance-sheet equality (tolerance env-configurable). Registration on the mandatory financials upload; server/gate.js persists statement_model + audit; advisory flags (non-template / unbalanced / missing) never block a submission. SubmitOpportunity.jsx 4b advisory card; sample fixtures carry balanced, projections-only and unbalanced models. Evidence: docs/evidence/W2-02/
FIN-03 | Financials & Returns | Return metrics under three scenarios | Must | Phase 1 | Built | W2 Financials | W2-03 | server/config/returnMetrics.js captures Equity IRR, ROIC and payback for base/upside/downside (all mandatory) and MOIC where relevant; evaluateReturnMetrics flags a missing downside and open cells without blocking. server/gate.js return_metrics on evaluateGate + returns config on GET /api/gate/fields; siriusMemo.js fills the page-4 returns table from the flat fields; SubmitOpportunity.jsx 4c advisory card. Evidence: docs/evidence/W2-03/
FIN-04 | Financials & Returns | Automatic hurdle test | Must | Phase 1 | Built | W2 Financials | W2-04 | server/config/hurdleTable.js evaluates every hurdle per captured scenario (Equity IRR >= 20%/greenfield 25%, ROIC >= WACC+5%, payback <= 3.5yrs, concentration <= 35%, leverage <= 3x) with a version stamp (HURDLE_TABLE_VERSION); thresholds come from mandate_threshold so an admin change moves the verdicts. server/gate.js hurdle_table on evaluateGate + GET /api/gate/fields; GET /api/themes/hurdles exposes the org policy; siriusMemo.js prints the live thresholds, per-scenario Meets? and a policy note; SubmitOpportunity.jsx 4e advisory card. Evidence: docs/evidence/W2-04/
FIN-05 | Financials & Returns | WACC input | Must | Phase 1 | Built | W2 Financials | W2-05 | server/config/wacc.js resolves the effective WACC (entity default from mandate_threshold.wacc_pct, env-overridable shipped default, or a reasoned per-opportunity override); an override without a reason is flagged override_valid:false and never applied silently. server/gate.js wacc on evaluateGate + config on GET /api/gate/fields; ThemeAdmin sets the entity WACC; SubmitOpportunity.jsx 4d card. Evidence: docs/evidence/W2-05/
FIN-06 | Financials & Returns | Financial sources and uses | Must | Phase 1 | Built | W2 Financials | W2-06 | server/config/sourcesUses.js captures each source (internal accruals, subsidiary debt, partner / co-investor, Sirius capital) with amount, % of total and status (secured/committed/indicative) and each use (purchase price, transaction costs, working capital, contingency); sources must equal uses (within a configurable tolerance) and Sirius capital is warned when drawn ahead of cheaper sources. server/gate.js sources_uses + GET /api/gate/fields; siriusMemo.js funding tables + balance note; SubmitOpportunity.jsx 5a card. Evidence: docs/evidence/W2-06/
FIN-07 | Financials & Returns | Budget status | Must | Phase 1 | Built | W2 Financials | W2-07 | server/config/budgetStatus.js confirms whether the opportunity is in the approved budget; off-budget requires a variance justification and makes a variance-memo upload (budget_confirmation) mandatory before submission, while an in-budget line reference is advisory. server/gate.js budget_status + submit-route block; siriusMemo.js budget note; SubmitOpportunity.jsx 5b card. Evidence: docs/evidence/W2-07/
FIN-08 | Financials & Returns | Cross-border considerations | Should | Phase 1 | Built | W2 Financials | W2-09 | server/config/crossBorder.js captures FX exposure, withholding tax, transfer pricing and repatriation restrictions for cross-border deals; the block applies only when the target geography names a different country from the owning subsidiary’s registered geography (canonicalCountry / isCrossBorder via GEOGRAPHY_TAGS), so a domestic deal is never asked. server/gate.js cross_border + GET /api/gate/fields; siriusMemo.js conditional Cross-border considerations table; SubmitOpportunity.jsx 4c card. Evidence: docs/evidence/W2-09/
FIN-09 | Financials & Returns | Entry valuation and exit | Must | Phase 1 | Built | W2 Financials | W2-08 | server/config/valuation.js captures the entry valuation as structured fields (EV / equity basis, amount, multiple, method) with a 3-5 name comparable set (nested valuation_comparables) and the exit / value-realisation route, timing and target multiple; a partial capture raises advisory flags (missing basis/method, comparable set below 3 or above 5, exit route without timing) and never blocks. server/gate.js valuation + GET /api/gate/fields; siriusMemo.js prints the comparable table and the entry/exit notes; SubmitOpportunity.jsx 4b card. Evidence: docs/evidence/W2-08/
FIN-10 | Financials & Returns | Deeper investment analytics | Could | Later phase | Deferred |  |  | BRD = Later phase
SCR-01 | Screening & Alignment | Automated initial screening panel | Must | Phase 1 | Built | W3 Screening | W3-01 | Single screening panel (W3-01): server/config/screeningPanel.js + GET /api/pipeline/opportunities/:id/screening renders all six checks (eligibility, hard filters, hurdle tests, alignment, synergy & conflict, completeness) with result, rationale and evidence refs on ScreeningBoard; evidence in docs/evidence/W3-01/
SCR-02 | Screening & Alignment | Strategy and theme alignment check | Must | Phase 1 | Built | W3 Screening | W3-13 | docs/evidence/W3-13/
SCR-03 | Screening & Alignment | Gate 1 hard filters | Must | Phase 1 | Built | W3 Screening | W3-02 | Gate 1 hard filters (W3-02): server/config/hardFilters.js evaluates the five Standing filters and raises Recommended decline with the reason; a reviewer with write access confirms or overrides with a written reason (audited), the screening panel check is a hard block on failure, and the capture form carries the six manual confirmations; evidence in docs/evidence/W3-02/
SCR-04 | Screening & Alignment | Gate 1 soft filters (1-5 scored) | Must | Phase 1 | Built | W3 Screening | W3-03 | Gate 1 soft filters (W3-03): server/config/softFilters.js scores the three soft filters 1-5 with a proposed score and rationale; a reviewer with write access confirms or adjusts every score with a reason (>=10 chars, audited), the scores roll up into a Strong/Moderate/Weak outcome and ride along on the screening panel without ever becoming a fail; evidence in docs/evidence/W3-03/
SCR-05 | Screening & Alignment | Automatic disqualifier flags | Must | Phase 1 | Built | W3 Screening | W3-04 | W3-04 docs/evidence/W3-04/
SCR-06 | Screening & Alignment | Synergy identification | Should | Phase 1 | Built | W3 Screening | W3-11 | docs/evidence/W3-11/
SCR-07 | Screening & Alignment | Portfolio conflict and concentration check | Should | Phase 1 | Built | W3 Screening | W3-10 | docs/evidence/W3-10/
SCR-08 | Screening & Alignment | Sanctions and adverse media screening | Should | Phase 1 | Built | W3 Screening | W3-12 | docs/evidence/W3-12/
SCR-09 | Screening & Alignment | Human-in-the-loop principle | Must | Phase 1 | Built | W3 Screening |  | workflows.js requires named actor
SCO-01 | Scorecard | Pre-screening quality score (0-100%) | Must | Phase 1 | Built | W3 Screening | W3-09 | docs/evidence/W3-09/
SCO-02 | Scorecard | Weighted 1-5 scorecard | Must | Phase 1 | Built | W3 Screening | W3-05 | W3-05 docs/evidence/W3-05/
SCO-03 | Scorecard | System-proposed scores | Should | Phase 1 | Built | W3 Screening | W3-07 | docs/evidence/W3-07/
SCO-04 | Scorecard | Two-lens floor | Should | Phase 1 | Built | W3 Screening | W3-06 | docs/evidence/W3-06/
SCO-05 | Scorecard | Scorecard configuration | Must | Phase 1 | Built | W3 Screening | W3-08 | docs/evidence/W3-08/
WF-01 | Workflow & Decisions | Phase 1 workflow states | Must | Phase 1 | Built | W6 Governance |  | PIPELINE_STATES/TRANSITIONS (pipeline.js)
WF-02 | Workflow & Decisions | Named owner and SLA | Must | Phase 1 | Built | W6 Governance |  | DEFAULT_SLA, owner, breach flag; m3/m4
WF-03 | Workflow & Decisions | Reviewer routing | Must | Phase 1 | Built | W6 Governance |  | workflows.js route/queue; ScreeningBoard.jsx
WF-04 | Workflow & Decisions | Built-in Q&A thread | Must | Phase 1 | Built | W6 Governance |  | qa.js threads/messages; tests m4
WF-05 | Workflow & Decisions | Review comments and decision reasons | Must | Phase 1 | Built | W6 Governance | W6-01 | docs/evidence/W6-01/
WF-06 | Workflow & Decisions | Related-party governance overlay | Must | Phase 1 | Built | W6 Governance | W6-03 | docs/evidence/W6-03/
WF-07 | Workflow & Decisions | Subsidiary presentation scheduling | Should | Phase 1 | Built | W6 Governance | W6-06 | Presentation scheduling captured on the opportunity record: date, attendees, status, format, outcome and next steps. Policy in AppSettings (presentation_session_config) with admin-edited revisions; org-scoped management (subsidiary owns its own, cross-org roles manage any); every create/update audited. Evidence: docs/evidence/W6-06/
WF-08 | Workflow & Decisions | Delegation of Authority routing (Gate 1) | Must | Phase 1 | Built | W6 Governance | W6-02 | docs/evidence/W6-02/
WF-09 | Workflow & Decisions | Full four-gate approval workflow | Must | Later phase | Deferred |  |  | BRD = Later phase (Phase 2)
OUT-01 | Screening Output | Initial Screening Memo | Must | Phase 1 | Built | W7 Reporting |  | siriusMemo.js, siriusMemoDocx.js, SiriusMemoDialog.jsx
OUT-02 | Screening Output | Opportunity Overview pack export | Should | Phase 1 | Built | W7 Reporting | W7-04 | server/memoPack.js + config/memoPack.js; six-page Part B pack (print-ready HTML + Markdown) with in_template_order manifest; export button behind MemoPack flag; tests memoPack (12) + m6 (6)
OUT-03 | Screening Output | QR verification on outputs | Should | Phase 1 | Built | W7 Reporting | W7-05 | server/memoVerification.js + config/memoVerification.js; signed QR (HMAC over id¦version¦hash¦issued_at) binds exported memo to record version + sha256 content fingerprint; public /verify recomputes live hash, tampered QR/record fails; QR embedded in .docx footer; tests memoVerification (12) + m6 (7)
OUT-04 | Screening Output | Investment memo auto-generation | Must | Later phase | Deferred |  |  | BRD = Later phase (Phase 3)
DSH-01 | Dashboards & Reporting | Investment Team pipeline dashboard | Must | Phase 1 | Built | W7 Reporting | W7-02 | server/pipelineDashboard.js + config/pipelineDashboard.js; src/pages/PipelineDashboard.jsx; filter set + drill-down; tests pipelineDashboard+m6
DSH-02 | Dashboards & Reporting | Subsidiary dashboard | Must | Phase 1 | Built | W7 Reporting |  | my-opportunities, Dashboard.jsx, org-scoped
DSH-03 | Dashboards & Reporting | IHC weekly report | Must | Phase 1 | Built | W7 Reporting | W7-01 | server/reporting.js + config/reporting.js; src/pages/Reporting.jsx; Excel/CSV export; tests reporting+m6
DSH-04 | Dashboards & Reporting | Funnel and cycle-time metrics | Should | Phase 1 | Built | W7 Reporting | W7-03 | server/pipelineMetrics.js + config/pipelineMetrics.js; src/pages/PipelineMetrics.jsx; funnel + cycle time vs SLA + decline reasons; tests pipelineMetrics+m6
DSH-05 | Dashboards & Reporting | Post-investment tracking | Must | Later phase | Deferred |  |  | BRD = Later phase (Phase 4)
AUD-01 | Audit Trail | Immutable audit log | Must | Phase 1 | Built | W6 Governance | W6-05 | Append-only audit_event (no-update trigger) plus a SHA-256 hash chain: each row stores prev_hash + a canonical hash of its fields, verifiable from genesis. writeAudit serialises chain appends under an advisory lock; POST /api/audit-chain/verify recomputes the chain end to end (admin-only, audited). Evidence: docs/evidence/W6-05/
AUD-02 | Audit Trail | Opportunity timeline | Must | Phase 1 | Built | W6 Governance |  | listAuditEvents, timeline; tests m1
AUD-03 | Audit Trail | Internal vs shared comments | Must | Phase 1 | Built | W6 Governance | W6-04 | Server-side visibility flag on qa_thread/qa_message; internal comments filtered from every read + notification for subsidiary-only users; no unit-test hits for the old internalComment name because visibility is carried on the row and enforced in qa.js. Evidence: docs/evidence/W6-04/
NTF-01 | Notifications | Event notifications | Must | Phase 1 | Built | W6 Governance | W6-07 | User-selectable notification email frequency (immediate or daily digest). Policy in AppSettings (notification_frequency_config) with an admin-edited revision; the choice is per-user on app_user; the delivery path defers email for a digest user and /digest composes only that user’s own rows, so entity isolation is preserved. Evidence: docs/evidence/W6-07/
ADM-01 | Configuration & Admin | Configurable rules | Must | Phase 1 | Built | W8 Platform | W8-03 | W8-03: unified admin config registry over 23 areas (7 groups); versioned (21) + audited (23); admin-only read/governance over the immutable audit trail; edits still flow through each area router so acceptance 'admin edits versioned + audited; applies only to new screenings'. Evidence: docs/evidence/W8-03/
ADM-02 | Configuration & Admin | Sector-specific variants | Could | Later phase | Deferred |  |  | BRD = Later phase
INTG-01 | Integration | Virtual data room integration | Should | Phase 1 | Built | W8 Platform | W8-04 | Folder link stored on the opportunity record (server/config/dataroomLink.js + pipeline routes + ScreeningBoard detail panel). evidence: docs/evidence/W8-04/
INTG-02 | Integration | Existing systems review | Must | Phase 1 | Process | W9 NFR/Release | W9-08 | discovery/documentation task
INTG-03 | Integration | Bulk import of in-flight opportunities | Should | Phase 1 | Built | W8 Platform | W8-05 | One-off bulk import of in-flight opportunities from the tracker spreadsheet with a validation report that names each row that cannot be loaded and why (server/config/bulkImport.js + server/xlsxRead.js + server/bulkImport.js routes + Settings Bulk Import tab). Evidence: docs/evidence/W8-05/
NFR-01 | Non-functional | Data residency and hosting | Must | Phase 1 | Process | W9 NFR/Release | W9-03 | Platform residency posture implemented and inspectable (server/config/residency.js + GET /api/health + Settings AI Governance panel; server/tests/residency.test.js 7 pass). Remaining item is the external UAE sovereign-hosting sign-off, a Sirius IT/security process activity recorded as an open go-live dependency (W9-02 control uae_data_residency). Blocked on that sign-off. Evidence: docs/evidence/W9-03/
NFR-02 | Non-functional | Security | Must | Phase 1 | Built | W9 NFR/Release | W9-02 | Security review and dependency advisory scan (NFR-02). server/config/securityPosture.js records the 13-control catalog and the accepted go-live scan; scripts/security_scan.mjs runs the server-runtime/production/full-tree audits, node --check over server/*.js and an injection-sink grep, exits non-zero on any open critical/high; npm audit fix cleared all critical/high (server runtime tree is 0 advisories). GET /api/ai-governance returns the posture and the AI Governance settings tab renders the gate, summary and control register. External go-live dependencies: independent pen test and UAE residency (W9-03). Evidence: docs/evidence/W9-02/
NFR-03 | Non-functional | AI governance | Must | Phase 1 | Built | W9 NFR/Release | W9-01 | server/config/aiGovernance.js owns the AI governance policy (prompt/response logging, email + secret redaction, AI-output labelling, provider approval, retention) and the provider register; server/aiGovernance.js exposes /api/ai-governance (policy + label + approval summary; admin PUT audited as entity ai_governance) plus the admin governed-call log; the LLM call path refuses an unapproved provider before the outbound call and logs a redacted, attributed row; src/components/shared/AIOutputBadge.jsx labels model output. Evidence: docs/evidence/W9-01/
NFR-04 | Non-functional | Performance | Should | Phase 1 | Built | W9 NFR/Release | W9-04 | Performance SIT (NFR-04). scripts/performance_sit.mjs measures P50/P95/max latency for the pipeline board, pipeline dashboard, funnel metrics, weekly reporting, portfolio register and a live screening panel, and exits non-zero when any endpoint misses the P95 budget or breaches the hard ceiling. server/config/performance.js holds the targets (P95 page budget 3000 ms, screening SLA 15 min) and the percentile/verdict helpers (unit-tested). Measured on 16,610 opportunity records: every endpoint P95 <= 44 ms, far inside the 3000 ms budget. Evidence: docs/evidence/W9-04/
NFR-05 | Non-functional | Availability and backup | Should | Phase 1 | Built | W9 NFR/Release | W9-05 | Backup/restore rehearsal (NFR-05). scripts/backup_restore_rehearsal.mjs drives a real pg_dump + scratch-database restore against the running container and reconciles the entity_record and audit_event counts; it exits non-zero on a count mismatch or an over-RTO restore. server/config/backupRestore.js holds the RPO 24h / RTO 8h gate (unit-tested). Rehearsal result: 37 MB dump, counts match exactly (16610 entity_record / 106098 audit_event), restore in ~5s vs the 8h RTO target. RUNBOOK.md documents the schedule and retention. Evidence: docs/evidence/W9-05/
NFR-06 | Non-functional | Browser and device support | Should | Phase 1 | Partial | W9 NFR/Release | W9-06 | Browser/device SIT (NFR-06). scripts/browser_sit.mjs drives the Dashboard, Deal Pipeline, Screening Board and Settings journeys through real Playwright browsers at desktop and tablet profiles and fails on a render or page error. server/config/browserSupport.js holds the support matrix and gate (unit-tested). Chrome/Edge (Chromium desktop) and tablet PASS; Safari / WebKit is not installable in this environment and is recorded as an external gap, not claimed as tested. Evidence: docs/evidence/W9-06/
NFR-07 | Non-functional | Usability | Must | Phase 1 | Partial | W9 NFR/Release | W9-07 | Guided six-section form, self-screen header seeding and save-as-draft exist (W1 evidence); no unaided-submission evidence yet. Usability gate + scorer implemented (server/config/usability.js, scripts/usability_uat.mjs, 8 unit tests) but the row stays Partial until a pilot UAT session is recorded. Blocked on pilot availability. See docs/evidence/W9-07/.
NFR-08 | Non-functional | Currency and units | Must | Phase 1 | Built | W9 NFR/Release | W2-10 | server/config/currency.js labels every financial figure with a currency and unit (AED mn base, USD mn where the mandate works in USD) and records the per-opportunity FX rate (AED per USD) so figures are reproducible against the base; the page-4 matrix, the on-screen memo and the exported DOCX all carry the label. server/gate.js currency + GET /api/gate/fields; SubmitOpportunity.jsx Reporting currency & FX rate card. Evidence: docs/evidence/W2-10/

## Backlog
TODO ID | Workstream | Title | BRD Req(s) | Priority | Size | Slice | Depends on | Owner | Acceptance criteria | Status | Effort (d) | Evidence
W1-01 | W1 Intake | Pre-form self-screen step (type, commitment, sector, geography, in-plan, related party) with stop messages | INT-02 | Must | M | S1 |  | Intake squad | Out-of-appetite types stop with reason; commitment < AED 10mn stops unless exception chosen | Done | 5 | code: server/config/selfScreen.js (six questions + evaluateSelfScreen, configured stops/flags/messages); server/gate.js GET /api/gate/fields self_screen, POST /api/gate/self-screen, submit blocked 422 + submit_blocked audit; src/pages/SubmitOpportunity.jsx pre-form self-screen step with locked capture form; src/api/client.js gate.selfScreen. test: server/tests/selfscreen.test.js (12 pass); server/tests/m2.test.js W1-01 gate block (18 pass). Evidence: docs/evidence/W1-01/preparer_self_screen_stop.png, docs/evidence/W1-01/preparer_self_screen_pass.png
W1-02 | W1 Intake | Below-floor exception route (synergy statement + IRR >= 35%), tagged and Sirius-escalated | INT-03 | Must | M | S1 | W1-01 | Intake squad | Exception requires both fields; case cannot close at subsidiary level | Done | 5 | code: server/config/belowFloor.js (BELOW_FLOOR_TAG/FIELDS/MESSAGES, BELOW_FLOOR_ESCALATION to Sirius, isBelowFloor, evaluateBelowFloor); selfScreen.js folds below_floor into the pre-form result; gate.js evaluateGate below_floor + submit 422 block (submit_blocked audit) + tagging (below_floor_exception/tag/escalated/escalated_at), pipeline_transition comment and notify below_floor_escalation to deal.lead@sirius.local; intakeConfig.js below_floor_synergy_case field; SubmitOpportunity.jsx below-floor-route / below-floor-tagged alerts; mvpSeed.js seed-below-floor + seed-below-floor-incomplete fixtures. test: server/tests/belowFloor.test.js (6 pass); server/tests/m2.test.js W1-02 route (3 pass, 21 total); full suite 177 pass. Evidence: docs/evidence/W1-02/preparer_below_floor_tagged.png, preparer_below_floor_route_incomplete.png, preparer_below_floor_submit_blocked.png
W1-03 | W1 Intake | Extend OPPORTUNITY_FIELDS to the six Opportunity Overview sections with per-section progress | INT-06 | Must | L | S1 |  | Intake squad | All six sections in fixed order; completion indicator per section; save-as-draft | Done | 10 | code: server/config/intakeConfig.js (6 sections, ~50 fields); server/gate.js OPPORTUNITY_FIELDS + GET /api/gate/fields; src/pages/SubmitOpportunity.jsx renders the model with per-section completion indicators (fixed group.key lookup). test: server/tests/intake.test.js (9 pass); commit 064caee. Evidence: docs/evidence/W1-03/preparer_six_section_form.png
W1-04 | W1 Intake | Accretion Statement structured mandatory fields | INT-07 | Must | S | S1 | W1-03 | Intake squad | Fields mandatory; rendered in screening memo | Done | 2 | code: intakeConfig.js accretion fields + OVERVIEW_SECTIONS.accretion; rendered in memo (server/siriusMemoDocx.js); test: server/tests/intake.test.js accretion case; commit 064caee. Evidence: docs/evidence/W1-04/preparer_accretion_statement.png
W1-05 | W1 Intake | Ten qualifying gates checklist, each Yes + evidence link, blocking submission on any No | INT-08 | Must | M | S1 | W1-03 | Intake squad | No blocks submission; evidence link required per gate | Done | 5 | code: server/config/qualifyingGates.js (10 BRD-ordered gates, evaluateQualifyingGates, gateAnswerKey); server/gate.js qualifying_gates in evaluateGate + /fields + submit-route 422 block (QUALIFYING_GATE_NOT_READY); UI http://.../ submit form qualifying-gates card with per-gate Yes/No + evidence ticks; test: server/tests/qualifyingGates.test.js (7); seed fixture seed-qualifying-no; Evidence: docs/evidence/W1-05/preparer_qualifying_gates_all_ready.png, preparer_qualifying_gate_no_blocked.png, preparer_qualifying_gate_submit_blocked.png
W1-06 | W1 Intake | CEO + CFO attestation gate (two named attestations, timestamp + IP, configurable text) | INT-09 | Must | M | S1 |  | Intake squad | Submission impossible until both recorded; each on audit log | Done | 5 | code: server/config/attestations.js (ATTESTATION_ROLES ceo/cfo + subsidiary variants, configurable ATTESTATION_SETTING_KEY='attestation_text' with DEFAULT_ATTESTATION_TEXTS, pure evaluateAttestations requiring by+at per role, attestationDefaults seed helper); server/gate.js loadAttestationTexts() reads AppSettings attestation_text, evaluateGate returns attestations, GET /api/gate/fields exposes attestations[], new POST /api/opportunities/:id/attestations/:key (role-authorized + canWriteOrg, draft/returned only, stores by/name/role/at/ip/text, audit attestation_recorded), submit route 422 block with ATTESTATION_REQUIRED_MESSAGE + submit_blocked audit; src/pages/SubmitOpportunity.jsx CEO & CFO attestation card with per-role signing; src/api/client.js gate.attest; mvpSeed.js fullFields attestations + seed-attestation-missing fixture (13 total). test: server/tests/attestations.test.js (8 pass); server/tests/m2.test.js W1-06 (4 pass, 25 total); full suite 198 pass; seedCleanup 5 pass. Evidence: docs/evidence/W1-06/preparer_attestations_all_ready.png, preparer_attestation_one_signed.png, preparer_attestation_submit_blocked.png
W1-07 | W1 Intake | Greenfield extra tests (benefit/why-now, budget status, secured funding, stage Concept/Feasibility/Initiate) | INT-10 | Must | M | S1 | W1-03 | Intake squad | Greenfield without secured funding blocked; Concept allows 2-page concept note only | Done | 5 | code: server/config/greenfield.js (GREENFIELD_STAGES Concept/Feasibility/Initiate, GREENFIELD_FIELDS greenfield_stage/benefit/secured_funding_source, GREENFIELD_THESIS_FIELDS, CONCEPT_NOTE_MAX_PAGES=2, pure evaluateGreenfield requiring stage + benefit + thesis + budget + a named SECURED source, greenfieldDefaults); server/config/intakeConfig.js greenfield_stage/benefit/secured_funding_source fields; server/gate.js evaluateGate greenfield (waives the document pack at Concept) + GET /api/gate/fields greenfield stages + submit-route 422 block (GREENFIELD_NOT_READY, submit_blocked audit); src/pages/SubmitOpportunity.jsx greenfield-tests / greenfield-tests-ready alerts; mvpSeed.js seed-greenfield (Concept, cleared) + seed-greenfield-unfunded (Feasibility, blocked), 14 fixtures. test: server/tests/greenfield.test.js (9 pass); server/tests/m2.test.js W1-07 (4 pass, 29 total); full suite 211 pass; seedCleanup 5 pass. Evidence: docs/evidence/W1-07/preparer_greenfield_tests_incomplete.png, preparer_greenfield_tests_ready.png, preparer_greenfield_submit_blocked.png
W1-08 | W1 Intake | Sourcing-channel side-effects: IHC/affiliate auto related-party flag; banker-led compressed-timeline indicator | INT-05 | Must | S | S1 |  | Intake squad | Flags auto-set and shown on every screen/output | Done | 2 | code: server/config/sourcingChannel.js (SOURCING_CHANNEL_FIELD, COMPRESSED_TIMELINE_CHANNEL/COMPRESSED_TIMELINE_TAG, RELATED_PARTY_TAG, pure evaluateSourcingChannel - mandatory channel, IHC/affiliate auto related-party flag via related_by_default, banker/advisor compressed-timeline indicator); server/gate.js sourcing_channel in evaluateGate + GET /api/gate/fields channels, submit 422 block on a missing/unrecognised channel, submit persists sourcing_tags + related_party_auto_flag + compressed_timeline; server/config/siriusMemo.js 'Sourcing channel' key fact + 'Sourcing side-effects' note; src/pages/SubmitOpportunity.jsx sourcing-channel-effects / sourcing-channel-required alerts; mvpSeed.js seed-banker-led fixture, 15 fixtures. test: server/tests/sourcingChannel.test.js (8 pass); server/tests/m2.test.js W1-08 (5 pass, 34 total); full suite 224 pass. Evidence: docs/evidence/W1-08/preparer_sourcing_affiliate_related_party.png, preparer_sourcing_banker_compressed_timeline.png
W1-09 | W1 Intake | Withdraw submission with reason; retained in history | INT-13 | Should | S | S1 |  | Intake squad | Withdrawn visible in history with reason | Done | 2 | code: server/pipeline.js withdrawn state (TRANSITIONS submission/returned to withdrawn), transition() requires a reason and records withdrawn_reason/withdrawn_at/withdrawn_by, opportunityToCard exposes withdrawn_reason + can_withdraw, board adds a Withdrawn column and my-opportunities excludes withdrawn from open; src/pages/ScreeningBoard.jsx Withdrawn column, reason-required dialog, withdraw offered only where can_withdraw. test: server/tests/m3.test.js W1-09 (4 pass). Evidence: docs/evidence/W1-09/preparer_withdraw_reason_dialog.png, preparer_withdrawn_in_history.png
W1-10 | W1 Intake | Duplicate detection warning to Investment Team (link/dismiss) | INT-12 | Could | M | S1 |  | Intake squad | Warns Investment Team only; subsidiary isolation preserved | Done | 5 | code: server/config/duplicates.js pure findDuplicates/compareOpportunities (same target/counterparty or similar name); server/duplicates.js /api/duplicates routes (Investment-Team-only) with duplicate_review link/dismiss, db.js duplicate_review table; pipeline.js board attaches duplicate_warning for cross-org readers only; src/api/client.js duplicates API; ScreeningBoard.jsx duplicate panel with link/dismiss; mvpSeed.js seed-duplicate-finstreet fixture. test: server/tests/duplicates.test.js (8 pass); server/tests/m3.test.js W1-10 (3 pass). Evidence: docs/evidence/W1-10/analyst_duplicate_warning.png, analyst_duplicate_dismissed.png
W2-01 | W2 Financials | Financial summary table FY-3..FY-1 + Y1-Y5 with derived ratios | FIN-01 | Must | L | S2 | W1-03 | Financials squad | Matches Part B p.4 layout; ratios auto-calculated; new ventures may leave actuals blank | Done | 10 | code: server/config/financials.js (FINANCIAL_PERIODS/ROWS, deriveFinancials, evaluateFinancials, isNewVenture); server/config/siriusMemo.js finTable from deriveFinancials; server/gate.js expose financials + evaluate on GET /api/gate/fields; src/pages/SubmitOpportunity.jsx financial grid (data-testid=financial-grid, fin-<row>-<period>); src/components/pipeline/SiriusMemoDialog.jsx memo-fin-table; mvpSeed.js seed-inf-vision matrix + greenfieldFinancials() for seed-greenfield. test: server/tests/financials.test.js (12 pass); siriusMemo.test.js finTable. Evidence: docs/evidence/W2-01/preparer_financial_summary_grid.png, preparer_financial_greenfield_blank_actuals.png, analyst_memo_financial_summary.png
W2-02 | W2 Financials | Three-statement model upload + presence/balance check | FIN-02 | Must | L | S2 | W2-01 | Financials squad | Missing statement / unbalanced BS raises flag; non-template flagged for manual review | Done | 10 | code: server/config/statementModel.js (THREE_STATEMENTS, BALANCE_SHEET_TOTALS, BALANCE_TOLERANCE_PCT, parseStatementModel, evaluateStatementModel, statementTemplateCsv); server/gate.js parse financials upload -> persist statement_model + statement_model_parsed audit + evaluateGate/GET /api/gate/fields; src/pages/SubmitOpportunity.jsx advisory 4b card (data-testid=statement-model-card, statement-model-status, statement-model-<key>, statement-model-balance, statement-model-flag/ok); server/config/mvpSeed.js balanced/greenfield/unbalanced models on fixtures. test: server/tests/statementModel.test.js (13 pass); server/tests/m2.test.js FIN-02 cases (template complete, unbalanced accepted+flagged, non-template accepted+flagged, parse audited). Evidence: docs/evidence/W2-02/preparer_statement_model_balanced.png, preparer_statement_model_greenfield.png, preparer_statement_model_flagged_unbalanced.png
W2-03 | W2 Financials | Return metrics equity IRR, ROIC, payback, MOIC for base/upside/downside | FIN-03 | Must | M | S2 | W2-01 | Financials squad | All three scenarios mandatory; downside required | Done | 5 | code: server/config/returnMetrics.js (RETURN_SCENARIOS base/upside/downside, RETURN_METRICS equity_irr/roic/payback required + moic where-relevant, returnsFromFlatFields, evaluateReturnMetrics); server/config/intakeConfig.js flat capture fields (none required); server/gate.js evaluateGate return_metrics + GET /api/gate/fields returns config; server/config/siriusMemo.js resolveReturns + MOIC hurdle row; src/pages/SubmitOpportunity.jsx advisory 4c card (data-testid=returns-scenarios-card, returns-scenarios-status, returns-row-<metric>, returns-cell-<metric>-<scenario>, returns-scenarios-downside, returns-scenarios-flag/ok); SiriusMemoDialog.jsx memo-returns-table; server/config/mvpSeed.js complete set on full-pack fixtures + base-only on seed-below-floor. test: server/tests/returnMetrics.test.js (8 pass); server/tests/m2.test.js FIN-03 cases (config, complete, downside-missing); siriusMemo.test.js flat-field case. Evidence: docs/evidence/W2-03/preparer_returns_three_scenarios.png, preparer_returns_downside_missing.png, analyst_memo_returns_scenarios.png
W2-04 | W2 Financials | Automatic hurdle table per scenario, admin-configurable + versioned | FIN-04 | Must | M | S2 | W2-03, W2-05 | Financials squad | Meets/Does-not-meet per hurdle per scenario; values versioned | Done | 5 | code: server/config/hurdleTable.js (HURDLE_TABLE_VERSION, HURDLE_META/HURDLE_DEFAULTS, hurdleThresholds resolving ROIC to WACC+spread, computeHurdles per-scenario with deal-level concentration/leverage, advisory below_hurdle/no_threshold flags); server/themes.js merges HURDLE_DEFAULTS into DEFAULT_THRESHOLDS + getHurdlePolicy + GET /api/themes/hurdles; server/gate.js hurdle_table on evaluateGate + versioned rows on GET /api/gate/fields; server/config/siriusMemo.js live thresholds + per-scenario Meets? + policy-version note in the page-4 returns table; src/pages/SubmitOpportunity.jsx advisory 4e card (data-testid=hurdle-table-card, hurdle-table-status, hurdle-row-<k>, hurdle-threshold-<k>, hurdle-cell-<k>-<s>, hurdle-passrate-<s>, hurdle-table-version, hurdle-table-flag/ok); leverage derived from a captured net-debt line via deriveFinancials. test: server/tests/hurdleTable.test.js (12 pass); server/tests/m2.test.js FIN-04 cases (config versioned, per-scenario verdicts, deal-level constants, below-hurdle flag, org policy); siriusMemo.test.js memo hurdle cases. Evidence: docs/evidence/W2-04/preparer_hurdle_table_per_scenario.png, preparer_hurdle_table_all_met.png, analyst_memo_hurdle_table.png
W2-05 | W2 Financials | WACC input per entity (Sirius-set) + per-opportunity override with reason | FIN-05 | Must | S | S2 |  | Financials squad | Default by entity; override requires reason | Done | 2 | code: server/config/wacc.js (WACC_DEFAULT_PCT env-overridable, WACC_OVERRIDE_FIELD/REASON_FIELD, WACC_OVERRIDE_REASON_MESSAGE, resolveWacc -> effective_wacc/source(entity_default¦opportunity_override¦system_default)/override_valid, meetsWaccSpread); server/db.js mandate_threshold.wacc_pct ALTER; server/themes.js DEFAULT_THRESHOLDS + getThresholds + upsertThresholds carry wacc_pct; server/gate.js resolveWacc on evaluateGate + wacc config on GET /api/gate/fields; server/config/intakeConfig.js wacc_override_pct + wacc_override_reason (not required); src/pages/ThemeAdmin.jsx Entity WACC threshold field; src/pages/SubmitOpportunity.jsx advisory 4d card (data-testid=wacc-card, wacc-status, wacc-effective, wacc-source, wacc-roic-summary, wacc-override-reason, wacc-flag); server/mvpSeed.js per-org entity WACC (Infinia 9, Finstreet 8.5, Sirius 7.5) merged onto operator thresholds; server/config/mvpSeed.js reasoned override on seed-theme-exception + reasonless override on seed-conflict. test: server/tests/wacc.test.js (7 pass); server/tests/m2.test.js FIN-05 cases (config, entity-default inheritance, reasoned override, reasonless flagged). Evidence: docs/evidence/W2-05/preparer_wacc_entity_default.png, preparer_wacc_override_with_reason.png, preparer_wacc_override_missing_reason.png
W2-06 | W2 Financials | Sources and uses table with status, sources = uses validation, funding-hierarchy warning | FIN-06 | Must | M | S2 |  | Financials squad | Sources must equal uses; warning when Sirius capital used ahead of cheaper sources | Done | 5 | code: server/config/sourcesUses.js (FUNDING_STATUSES secured/committed/indicative, SOURCE_ROWS subsidiary_accruals/subsidiary_debt/partner_co_investor/sirius_capital, USE_ROWS purchase_price/transaction_costs/working_capital/contingency, BALANCE_TOLERANCE_PCT env-overridable, evaluateSourcesUses -> rows with aed/%/status, totals, difference, balanced, sirius_ask_aed, hierarchy {order,violation,ahead_of}, flags [sources_not_uses¦funding_hierarchy¦invalid_status]); server/gate.js sources_uses on evaluateGate + config on GET /api/gate/fields; server/config/siriusMemo.js funding tables built from the plan (source row with AED mn/%/status + totals, uses + total, balance note); src/pages/SubmitOpportunity.jsx 5a card (data-testid=sources-uses-card, sources-uses-status, source-row-<k>, source-aed-<k>, source-pct-<k>, source-status-<k>, use-row-<k>, use-aed-<k>, sources-uses-total-sources, sources-uses-total-uses, sources-uses-difference, sources-uses-flag, sources-uses-hierarchy-flag, sources-uses-ok); SiriusMemoDialog.jsx memo-funding-tables. test: server/tests/sourcesUses.test.js (10 pass); server/tests/m2.test.js FIN-06 cases (config, balanced, imbalanced flag, hierarchy flag, cheaper-secured-first no flag). Evidence: docs/evidence/W2-06/preparer_sources_uses_balanced.png, preparer_sources_uses_hierarchy_flag.png, analyst_memo_sources_uses.png
W2-07 | W2 Financials | Budget status with variance-memo enforcement on No | FIN-07 | Must | S | S2 |  | Financials squad | No makes variance memo upload mandatory | Done | 2 | code: server/config/budgetStatus.js (BUDGET_FIELDS in_approved_budget/budget_status/budget_line_reference/variance_justification, VARIANCE_MEMO_KEY=budget_confirmation, BUDGET_STATUS_VALUES in_budget/variance_justified, evaluateBudgetStatus -> applies/answered/in_budget/off_budget/budget_status/line_reference/justification/variance_memo_required/variance_memo_present/satisfied, stops [budget_answer_required¦variance_justification_required¦variance_memo_required], flags [budget_line_missing]); server/gate.js budget_status on evaluateGate + off-budget variance memo pushed into missing + config on GET /api/gate/fields + submit-route 422 submit_blocked block; server/config/intakeConfig.js budget_line_reference + variance_justification (not required); server/config/siriusMemo.js budget note from the same evaluation; src/pages/SubmitOpportunity.jsx 5b card (data-testid=budget-status-card, budget-status-badge, budget-line-reference, budget-variance, budget-variance-memo, budget-status-flag, budget-status-line-flag, budget-status-ok). test: server/tests/budgetStatus.test.js (8 pass); server/tests/m2.test.js FIN-07 cases (config, in-budget satisfied, off-budget blocked + missing memo, off-budget satisfied with justification + memo). Evidence: docs/evidence/W2-07/preparer_budget_status_in_budget.png, preparer_budget_status_off_budget.png, analyst_memo_budget_status.png
W2-08 | W2 Financials | Entry valuation & exit structured fields (EV, multiple, method, 3-5 comps, exit route) | FIN-09 | Must | M | S2 |  | Financials squad | Structured capture; comps 3-5 | Done | 5 | code: server/config/valuation.js (VALUATION_BASIS ev/equity, VALUATION_METHODS trading_comps/precedent_transactions/dcf/asset_based/other, COMPARABLE_MIN=3/COMPARABLE_MAX=5, VALUATION_FIELDS basis/amount/multiple/method/comparables/exit_route/exit_timing/exit_multiple, evaluateValuation -> entry {amount,basis,basis_valid,multiple,method,method_valid,present,complete}, comparables[], comparable_count, comparables_ok, exit {route,timing,multiple,present,complete}, captured, complete, flags [entry_amount_missing¦entry_basis_missing¦entry_method_missing¦comps_incomplete¦comps_too_many¦exit_incomplete], message); server/config/intakeConfig.js entry_valuation_basis + entry_valuation_method (selects) + exit_multiple (number), none required; server/gate.js valuation on evaluateGate + config on GET /api/gate/fields; server/config/siriusMemo.js Entry valuation & comparable set table (padded to >=3 rows) + entry-basis and exit notes; src/pages/SubmitOpportunity.jsx 4b card (data-testid=valuation-card, valuation-status, valuation-entry-basis/amount/multiple/method, valuation-comparable-row-<i>/name-<i>/metric-<i>/multiple-<i>, valuation-exit-route/timing/multiple, valuation-flag, valuation-ok) with the seven flat keys filtered out of the generic section loop; SiriusMemoDialog.jsx generic table testid (memo-valuation-table). test: server/tests/valuation.test.js (10 pass); server/tests/m2.test.js FIN-09 cases (config exposes fields + comparable bounds, complete capture no flags, below-minimum flagged not blocked). Evidence: docs/evidence/W2-08/preparer_valuation_complete.png, preparer_valuation_incomplete_flag.png, analyst_memo_valuation_table.png
W2-09 | W2 Financials | Cross-border fields (FX, WHT, transfer pricing, repatriation), conditional on geography | FIN-08 | Should | S | S2 |  | Financials squad | Fields appear when target geography differs from home country | Done | 2 | code: server/config/crossBorder.js (CROSS_BORDER_FIELDS fx/wht/transfer_pricing/repatriation, CROSS_BORDER_ITEMS in BRD order, canonicalCountry + isCrossBorder mapping free-text geography onto a country via GEOGRAPHY_TAGS so UAE==United Arab Emirates, evaluateCrossBorder(data,{homeCountry}) -> applies/target_country/home_country/items[{key,label,short,value,present}]/captured/total/complete/flags[<short>_missing]/message); server/gate.js cross_border on evaluateGate (home country via getOrganization(ownerOrg).geography) + config on GET /api/gate/fields; server/config/intakeConfig.js cross_border_fx/wht/transfer_pricing/repatriation (textareas, not required); server/config/siriusMemo.js Cross-border considerations table + target-vs-home note only when applies (homeCountry threaded through ctx); src/pages/SubmitOpportunity.jsx 4c card (data-testid=cross-border-card, cross-border-status, cross-border-fx/wht/transfer-pricing/repatriation, cross-border-flag, cross-border-ok) rendered only when the gate applies, four flat keys filtered out of the generic loop; fixture seed-cross-border (India target, UAE Infinia home). test: server/tests/crossBorder.test.js (10 pass); server/tests/m2.test.js FIN-08 cases (config exposes fields+items, same-country not applies, cross-country all-four complete, partial flagged not blocked). Evidence: docs/evidence/W2-09/preparer_cross_border_complete.png, preparer_cross_border_not_applicable.png, analyst_memo_cross_border.png
W2-10 | W2 Financials | Per-opportunity FX rate capture attached to financial fields | NFR-08 | Must | S | S2 | W2-01 | Financials squad | Currency/unit shown on every financial field; FX recorded | Done | 2 | code: server/config/currency.js (BASE_CURRENCY AED, BASE_UNIT mn, REPORTING_CURRENCIES AED/USD, CURRENCY_FIELDS reporting_currency + fx_rate_usd_aed, normaliseCurrency defaults to AED, evaluateCurrency -> currency/unit/is_base/fx_rate/fx_required/fx_present/fx_valid/base_currency/label/rate_label/complete/flags[fx_rate_missing¦fx_rate_invalid]/message, toBaseCurrency converts USD->AED at the recorded rate or null); server/gate.js currency on evaluateGate + config on GET /api/gate/fields; server/config/intakeConfig.js reporting_currency (select) + fx_rate_usd_aed (number), neither required; server/config/siriusMemo.js finTable headed "Financials (<label>)" with unit column = label + Reporting currency & units note; server/siriusMemoDocx.js + SiriusMemoDialog.jsx render the label; src/pages/SubmitOpportunity.jsx Reporting currency & FX rate card at the top of the financials section (data-testid=currency-card, currency-status, currency-select, currency-fx-rate, currency-unit-note, currency-flag, currency-ok), 4a heading reads the chosen currency + unit, rate field disabled on the base currency, two flat keys filtered out of the generic loop; fixtures seed-fx-usd (USD @ 3.6725) + seed-fx-missing (USD, no rate). test: server/tests/currency.test.js (8 pass); server/tests/m2.test.js NFR-08 cases (config exposes base currency + field names, default AED complete no flags, USD with rate complete, USD without rate flagged not blocked). Evidence: docs/evidence/W2-10/preparer_currency_complete_usd.png, preparer_currency_default_aed.png, preparer_currency_flag_missing_rate.png, analyst_memo_currency_label.png
W3-01 | W3 Screening | Single screening panel aggregating eligibility, hard filters, hurdles, alignment, synergy/conflict, completeness | SCR-01 | Must | L | S3 | W2-02, W2-04 | Screening squad | Runs within 15 min of submission; each check shows result, rationale, evidence ref | Done | 10 | code: server/config/screeningPanel.js (SCREENING_CHECKS six BRD checks in order, SCREENING_SLA_MINUTES 15, advisory SCREENING_DISCLAIMER, evaluateScreeningPanel({gate,alignment,duplicates,conflict}) -> checks[{key,module,label,order,advisory,result pass¦flag¦fail¦not_applicable,pending,status,rationale,evidence_refs,detail}] + summary{counts,blocking,flagged,advisory_open,recommended,complete} + complete/flags/message, composes the existing gate blocks (self_screen, below_floor, hurdle_table, statement_model, currency, missing, completeness) + alignment score, hard filters & synergy marked advisory, missing theme / unentered returns = pending not false verdict, never-rejects SCR-09); server/pipeline.js GET /opportunities/:id/screening (404/403 org-visibility, duplicates for cross-org readers only); src/api/client.js api.pipeline.screening(id); src/pages/ScreeningBoard.jsx screening panel at top of detail sheet (data-testid=screening-panel + screening-check-<key>) with result badges, advisory marker, evidence chips + i18n board.initialScreening. test: server/tests/screeningPanel.test.js (10 pass); server/tests/m3.test.js W3-01 cases (5 pass: panel shape + result/rationale/evidence per check + advisory disclaimer, submitted opportunity complete, stopped self-screen fails eligibility, sibling 403, missing 404). Evidence: docs/evidence/W3-01/analyst_screening_panel_overview.png, analyst_screening_panel_alignment_flag.png, analyst_screening_panel_conflict_signals.png
W3-02 | W3 Screening | Gate 1 hard filters -> Recommended decline, reviewer confirm/override | SCR-03 | Must | M | S3 | W3-01 | Screening squad | Failed filter sets Recommended decline with reason; system never rejects alone | Done | 5 | code: server/config/hardFilters.js (HARD_FILTER_VERSION HF-01.1, HARD_FILTER_ITEMS five Standing filters in BRD order - designated_vertical / check_size / sanctions_export / structuring / portfolio_conflict, HARD_FILTER_FIELDS six manual inputs, HARD_FILTER_REVIEW_DECISIONS confirmed¦overridden + REASON_MIN 10, evaluateHardFilters(data,{theme,thresholds}) -> items[{key,label,group,order,manual,status pass¦fail¦flag¦not_evaluated,pending,rationale,evidence_refs,detail}]/failed[]/pending[]/recommended_outcome/recommended_reason/effective_outcome/review/awaiting_review/complete/flags/message, buildHardFilterReview validates a review and requires a written reason); server/config/intakeConfig.js six non-required hard-filter fields in the risks section (14-key required minimum unchanged); server/gate.js hard_filters on evaluateGate (effective theme resolved for the owner org) + config on GET /api/gate/fields + POST /opportunities/:id/hard-filter-review (write-org 403, 409 when nothing failed, decision persisted + audited hard_filter_<decision>) + GET /opportunities/:id/hard-filter-review/history; server/config/screeningPanel.js hard_filters check advisory:false reading the gate block (fail->Fail, flagged manual->Flag, else Pass); src/api/client.js gate.reviewHardFilter; src/pages/SubmitOpportunity.jsx 6a hard-filters card (hard-filters-card, hard-filter-<key>, hard-filter-sanctions/structuring/portfolio-conflict + notes + conflict-reviewer, hard-filters-outcome, hard-filters-decline); src/pages/ScreeningBoard.jsx reviewer confirm/override control (hard-filter-review, hard-filter-decision-confirmed/overridden, hard-filter-reason, hard-filter-submit). test: server/tests/hardFilters.test.js (17 pass); server/tests/screeningPanel.test.js (11 pass incl. failed filter -> Fail + recommended decline); server/tests/m3.test.js W3-02 cases (4 pass: five filters with outcomes, /fields config, failed filter -> recommended_decline + override needs reason + short reason 400, sibling 403 + clean deal 409). Evidence: docs/evidence/W3-02/preparer_hard_filters_form.png, analyst_hard_filters_recommended_decline.png, reviewer_hard_filters_review_override.png
W3-03 | W3 Screening | Gate 1 soft filters scored 1-5 with proposed score + rationale | SCR-04 | Must | M | S3 | W3-01 | Screening squad | Each soft filter scored; reviewer confirms | Done | 5 | code: server/config/softFilters.js (SOFT_FILTER_VERSION SF-01.1, SOFT_FILTER_ITEMS three scored soft filters in BRD order - portfolio_adjacency / national_priorities / management_openness, SOFT_FILTER_FIELDS four manual inputs, SOFT_FILTER_SCALE 1-5, SOFT_FILTER_OUTCOMES strong¦moderate¦weak, UAE_PRIORITY_SECTORS, evaluateSoftFilters(data,{theme,portfolio,nationalPriorities}) -> items[{key,label,group,order,proposed_score,proposed_label,score,label_band,confirmed,adjusted,rationale,evidence_refs,detail}]/item_count/proposed_average/average/average_label/outcome/review/awaiting_review/complete/flags/message, buildSoftFilterReview validates a review and requires all three scores 1-5 plus a rationale >=10 chars); server/config/intakeConfig.js four non-required soft-filter fields in the risks section (14-key required minimum unchanged); server/gate.js soft_filters on evaluateGate (theme/portfolio/national-priorities inputs) + config on GET /api/gate/fields + POST /opportunities/:id/soft-filter-review (write-org 403, decision persisted + audited soft_filter_<decision>) + GET /opportunities/:id/soft-filter-review/history; server/config/screeningPanel.js soft_filters ride along as a section, not one of the six checks; src/api/client.js gate.reviewSoftFilter; src/pages/SubmitOpportunity.jsx 6b soft-filters card (soft-filters-card, soft-filter-<key>, soft-filter-management-openness + notes, soft-filters-outcome, soft-filters-scale); src/pages/ScreeningBoard.jsx reviewer confirm/adjust control (soft-filter-review, soft-filter-row-<key>, soft-filter-score-<key>-<n>, soft-filter-rationale-<key>, soft-filter-submit). test: server/tests/softFilters.test.js (10 pass); server/tests/screeningPanel.test.js (12 pass incl. soft filters ride-along section); server/tests/m3.test.js W3-03 cases (4 pass: three scored filters + proposed scores + awaiting_review, /fields config, short rationale 400 + bad score 400 + reasoned decision 200 confirms/adjusts + audit history + re-read persists, sibling 403). Evidence: docs/evidence/W3-03/preparer_soft_filters_form.png, analyst_soft_filters_scored_not_declined.png, reviewer_soft_filters_review_adjust.png
W3-04 | W3 Screening | Disqualifier flags with named clear + reason | SCR-05 | Must | M | S3 | W3-02 | Screening squad | Flag prominent on record and memo; clearing needs reviewer + reason | Done | 5 | docs/evidence/W3-04/ - preparer form, analyst 2-open-flags, reviewer named clear; server/tests/disqualifiers.test.js 11 pass, m3 4 cases
W3-05 | W3 Screening | Weighted 1-5 scorecard from Gate 2 criteria; weights sum 100%; >= 3.5 to proceed | SCO-02 | Must | L | S3 | W3-03 | Screening squad | Weights validated to 100%; guide text per criterion; total/outcome auto | Done | 10 | docs/evidence/W3-05/ - weighted summary, criteria scoring, CIO override below bar; server/tests/scorecard.test.js 12 pass, m3 3 cases
W3-06 | W3 Screening | Two-lens floor (strategic vs financial sub-totals) | SCO-04 | Should | M | S3 | W3-05 | Screening squad | Sub-totals shown; below floor if either under floor | Done | 5 | docs/evidence/W3-06/
W3-07 | W3 Screening | System-proposed scores per criterion (proposed + final stored; comment on adjustment) | SCO-03 | Should | M | S3 | W3-05 | Screening squad | Both stored; comment required on adjustment | Done | 5 | docs/evidence/W3-07/
W3-08 | W3 Screening | Scorecard configuration admin (criteria, weights, thresholds, guide text), versioned | SCO-05 | Must | M | S3 | W3-05 | Screening squad | Versioned + audited; historical scores not silently recalculated | Done | 5 | docs/evidence/W3-08/
W3-09 | W3 Screening | Overall quality score 0-100% with component breakdown and configurable bands | SCO-01 | Must | M | S3 | W3-05 | Screening squad | Breakdown shown; advisory only; bands configurable | Done | 5 | docs/evidence/W3-09/
W3-10 | W3 Screening | Portfolio conflict & concentration check against register | SCR-07 | Should | M | S3 | W4-01 | Screening squad | Conflict flags with affected company; concentration % where data exists | Done | 5 | docs/evidence/W3-10/
W3-11 | W3 Screening | Synergy identification against portfolio register | SCR-06 | Should | M | S3 | W4-01 | Screening squad | Top synergies listed; marked requires operating-company sign-off | Done | 5 | docs/evidence/W3-11/
W3-12 | W3 Screening | Sanctions / adverse media manual confirmation field + evidence upload | SCR-08 | Should | S | S3 |  | Screening squad | Confirmation field with evidence on record | Done | 2 | docs/evidence/W3-12/
W3-13 | W3 Screening | Theme alignment document-passage citation (rationale quotes source doc) | SCR-02 | Must | M | S3 | W4-02 | Screening squad | Per-dimension Aligned/Partly/Not aligned with rationale citing source passage | Done | 5 | docs/evidence/W3-13/
W4-01 | W4 Entity | Portfolio register seeded from BRD list with cluster/sector/geography/capability tags | ENT-04 | Must | M | S4 |  | Data squad | Register loadable from template; each record has sector/geo/capability tags | Done | 5 | docs/evidence/W4-01/
W4-02 | W4 Entity | Strategy document upload + indexing feeding the alignment engine within 10 min | ENT-02 | Must | M | S4 |  | Data squad | PDF/DOCX/PPTX indexed and available to alignment | Done | 5 | docs/evidence/W4-02/
W4-03 | W4 Entity | Versioned entity strategy profile; version recorded per screening | ENT-01 | Must | M | S4 | W4-02 | Data squad | Profile versioned; version used recorded per screening | Done | 5 | docs/evidence/W4-03/
W4-04 | W4 Entity | Versioned Sirius mandate admin-editable | ENT-03 | Must | S | S4 |  | Data squad | Changes versioned + audited | Done | 2 | docs/evidence/W4-04/
W5-01 | W5 Documents | Checklist generation by type/stage/flags with mandatory/conditional/optional, admin-maintainable | DOC-01 | Must | M | S4 | W1-03 | Intake squad | Checklist updates as answers change; admin edits without code | Done | 5 | docs/evidence/W5-01/
W5-02 | W5 Documents | Version history + virus scan on upload; 50 MB limit, PDF/DOCX/XLSX/PPTX | DOC-02 | Must | M | S4 |  | Intake squad | Previous versions retained; scan on upload | Done | 5 | docs/evidence/W5-02/
W5-03 | W5 Documents | Content sufficiency check (missing cash flow, < 3y history, no downside) - advisory | DOC-04 | Should | L | S4 | W2-02 | Intake squad | Flags to preparer pre-submit and reviewer post; override with reason | Done | 10 | docs/evidence/W5-03/
W5-04 | W5 Documents | Data-point to source mapping (config-held; click to open source) | DOC-05 | Should | M | S4 | W2-01 | Intake squad | Mapping in config; reviewer opens linked source | Done | 5 | docs/evidence/W5-04/
W5-05 | W5 Documents | Templates area (Opportunity Overview, model, risk register, gate checklist) | DOC-06 | Should | S | S4 |  | Intake squad | Current versions downloadable, Investment-Team maintained | Done | 2 | docs/evidence/W5-05/
W6-01 | W6 Governance | Configurable decision reason codes + free text; decisions unsaveable without reason | WF-05 | Must | S | S5 |  | Governance squad | Reason required; declines captured for comparables | Done | 2 | docs/evidence/W6-01/
W6-02 | W6 Governance | Delegation of Authority thresholds by ticket size for Gate 1 RACI | WF-08 | Must | M | S5 |  | Governance squad | RACI enforced at Gate 1 | Done | 3 | docs/evidence/W6-02/
W6-03 | W6 Governance | Related-party overlay hardening: conflicted-user exclusion, arm's-length documentation gate | WF-06 | Must | M | S5 |  | Governance squad | Case cannot reach Screening Decision without independent sign-off; conflicted users ineligible | Done | 5 | docs/evidence/W6-03/
W6-04 | W6 Governance | Internal vs shared comments visibility flag | AUD-03 | Must | M | S5 |  | Governance squad | Internal comments never visible to subsidiary roles | Done | 4 | code: server/config/commentVisibility.js + commentVisibilityData.js (visibilities shared/internal, subsidiary roles, mayViewVisibility/isSubsidiaryViewer/effectiveMessageVisibility); server/commentVisibility.js GET/PUT /api/comment-visibility + history; server/qa.js filters every read + refuses internal authoring by a subsidiary role + drops subsidiary recipients from internal notifications; qa_thread.visibility + qa_message.visibility columns (db.js); Settings Comment Visibility tab; Q&A and opportunity-route Internal badges + internal toggle. test: server/tests/commentVisibility.test.js (11 pass); server/tests/m6.test.js W6-04 (6 pass); full suite 789 pass. Evidence: docs/evidence/W6-04/
W6-05 | W6 Governance | Hash-chained, tamper-evident audit over append-only audit_event | AUD-01 | Must | M | S5 |  | Governance squad | Log verifiable; tamper detected; 100% gate actions logged | Done | 5 | code: server/config/auditChainData.js + auditChain.js (canonicalize/canonicalRow/computeRowHash/verifyChain, sha256, genesis DEALFORGE-AUDIT-GENESIS-V1, config resolve/validate/build/diff); server/audit.js writeAudit stores seq/prev_hash/hash inside pg_advisory_xact_lock transaction + verifyAuditChain(); server/auditChain.js GET/PUT /api/audit-chain + POST /verify (admin-only, audited) + /history; db.js AUDIT_CHAIN_SCHEMA (seq/prev_hash/hash + partial unique index); Settings Audit Integrity tab + api.auditChain. test: server/tests/auditChain.test.js (13 pass); server/tests/m6.test.js W6-05 (6 pass); full suite 808 pass. Evidence: docs/evidence/W6-05/
W6-06 | W6 Governance | Presentation scheduling capture (date, attendees, outcome, next steps) | WF-07 | Should | S | S5 |  | Governance squad | Captured on record | Done | 2 | code: server/config/presentationSessionsData.js + presentationSessions.js (defaultPresentationConfig/validate/resolve/diff/build/normaliseSession/mayManagePresentations); server/db.js PRESENTATION_SCHEMA (presentation_session table + indexes); server/presentationSessions.js /api/presentations (policy GET/PUT admin-audited + /history + opportunity-scoped session list/create/update, 422 on missing field, outcome-required-on-complete); OpportunityRoute.jsx Presentation scheduling panel + api.presentations. test: server/tests/presentationSessions.test.js (11 pass); server/tests/m6.test.js W6-06 (6 pass); full suite 825 pass. Evidence: docs/evidence/W6-06/
W6-07 | W6 Governance | Notification email frequency (immediate / daily digest) | NTF-01 | Must | S | S5 |  | Governance squad | User-selectable frequency; entity isolation respected | Done | 2 | code: server/config/notificationFrequencyData.js + notificationFrequency.js (defaultNotificationFrequencyConfig/validate/resolve/diff/build/effectiveFrequency/validateUserPreference/composeDigest); server/db.js NOTIFICATION_FREQUENCY_SCHEMA (app_user.notification_frequency); server/notificationFrequency.js /api/notification-frequency (policy GET + per-user PUT 422 on bad value + /policy admin PUT audited + /policy-history + /digest); server/notify.js defers email for a digest user (status deferred); Settings Notifications tab + api.notificationFrequency. test: server/tests/notificationFrequency.test.js (10 pass); server/tests/m6.test.js W6-07 (6 pass); full suite 841 pass. Evidence: docs/evidence/W6-07/
W7-01 | W7 Reporting | IHC weekly report reproducing Friday tracker columns, Excel export, optional weekly schedule | DSH-03 | Must | L | S6 |  | Reporting squad | Columns match agreed tracker; exportable; schedulable | Done | 6 | evidence: docs/evidence/W7-01/leadership_ihc_weekly_tracker_leadership.png, admin_ihc_reporting_configuration_admin.png; code: server/config/reportingData.js + reporting.js, server/reporting.js, server/xlsx.js, src/pages/Reporting.jsx; tests: server/tests/reporting.test.js (10), m6.test.js W7-01 (5); full suite 856 pass
W7-02 | W7 Reporting | Pipeline dashboard filters (entity, cluster, sector, state, owner, date) + drill-down | DSH-01 | Must | M | S6 |  | Reporting squad | Filters + drill-down; near-real-time | Done | 5 | evidence: docs/evidence/W7-02/leadership_pipeline_dashboard_filters_leadership.png, leadership_pipeline_dashboard_drilldown_leadership.png; code: server/config/pipelineDashboardData.js + pipelineDashboard.js, server/pipelineDashboard.js, src/pages/PipelineDashboard.jsx; tests: server/tests/pipelineDashboard.test.js (12), m6.test.js W7-02 (6); full suite 874 pass
W7-03 | W7 Reporting | Funnel & cycle-time metrics (conversion by stage, decline reasons, avg time/state vs SLA) | DSH-04 | Should | M | S6 | W7-02 | Reporting squad | Metrics for any date range; cycle time vs SLA | Done | 5 | evidence: docs/evidence/W7-03/leadership_funnel_conversion_leadership.png, leadership_cycle_time_vs_sla_leadership.png; code: server/config/pipelineMetricsData.js + pipelineMetrics.js, server/pipelineMetrics.js, src/pages/PipelineMetrics.jsx; tests: server/tests/pipelineMetrics.test.js (11), m6.test.js W7-03 (5); full suite 890 pass
W7-04 | W7 Reporting | Opportunity Overview pack export (six-page Part B order/layout) | OUT-02 | Should | L | S6 | W1-03 | Reporting squad | Export follows Part B page order | Done | 10 | evidence: docs/evidence/W7-04/preparer_export_overview_pack_button.png, preparer_pack_six_page_part_b_order.png; code: server/config/memoPackData.js + memoPack.js, server/memoPack.js, src/components/pipeline/SiriusMemoDialog.jsx export button; tests: server/tests/memoPack.test.js (12), m6.test.js W7-04 (6); full suite 908 pass
W7-05 | W7 Reporting | QR verification on exported memos linking to record version + hash | OUT-03 | Should | M | S6 | W6-05 | Reporting squad | Authorised scan opens record version/hash; tampered copy fails | Done | 5 | evidence: docs/evidence/W7-05/preparer_verification_qr_panel.png, preparer_verify_page_match.png, preparer_verify_page_tampered.png; code: server/config/memoVerificationData.js + memoVerification.js, server/memoVerification.js, server/siriusMemoDocx.js QR footer, src/pages/VerifyMemo.jsx /verify route, memo dialog QR panel; tests: server/tests/memoVerification.test.js (12), m6.test.js W7-05 (7); full suite 927 pass
W8-01 | W8 Platform | SSO (OIDC/SAML) + MFA provider integration; local accounts for approved externals | PLT-04 | Must | L | S7 |  | Platform squad | SSO works for Sirius + pilot subsidiary; MFA enforced; failed logins logged | Done | 10 | code: server/config/authPolicyData.js + server/config/authPolicy.js (MFA modes, OIDC/SAML kinds, SSO_PROVIDERS env, provider validation/redaction/merge, mfaRequiredForRoles/isLocalDomainAllowed/providerForDomain/sessionMfaSatisfied); server/authPolicy.js router /api/auth-policy (GET policy + history, PUT policy, POST/DELETE providers, admin via canConfigure, audited + persisted to AppSettings); server/auth.js Better Auth twoFactor + sso plugins, before-hook local-domain allowlist gate, after-hooks audit sign_in / sign_in_mfa_challenge / sign_in_failed / TOTP; server/index.js app-wide enforce_mfa middleware (403 mfa_required); src/pages/SuperAdmin.jsx Security & SSO tab; src/pages/Login.jsx Sign in with SSO. test: server/tests/authPolicy.test.js (20 pass); server/tests/auth.test.js PLT-04 suite (30 pass combined). Evidence: docs/evidence/W8-01/admin_auth_policy_mfa.png, admin_sso_provider_registry.png, admin_login_sso_button.png
W8-02 | W8 Platform | i18n completion: all UI strings externalised; RTL demonstrated on >= 1 screen | PLT-06 | Should | M | S7 |  | Platform squad | No hard-coded strings; RTL demo screen | Done | 5 | code: src/lib/i18nMessages.js (shared en/ar dictionaries; Arabic authors chrome, vocabulary and the Dashboard); server/config/i18nData.js (LOCALES with dir/native label, DEFAULT_LOCALE, RTL_DEMO_SCREEN=/Dashboard, CORE_KEYS) + server/config/i18n.js (normaliseLocale, directionFor/isRtl, missingCoreKeys, localeSummary, buildI18nPayload); server/i18n.js /api/i18n + /api/i18n/locales; src/lib/i18n.jsx reads shared dicts and flips document lang/dir; src/pages/Dashboard.jsx + dashboard panels fully translated via t(). test: server/tests/i18n.test.js (14 pass, 53/53 core keys both locales); server/tests/i18nApi.test.js (2 pass). Evidence: docs/evidence/W8-02/admin_dashboard_ltr.png, admin_dashboard_rtl.png
W8-03 | W8 Platform | Unified admin config for hurdles, thresholds, weights, checklist, routing, SLAs, reason codes, picklists | ADM-01 | Must | L | S7 | W2-04, W3-08, W6-01 | Platform squad | Admin edits versioned + audited; applies only to new screenings | Done | 10 | code: server/config/adminConfigData.js (23 configurable areas in 7 groups with key/action/route/code + versioned/audited flags, ADMIN_CONFIG_VERSION=ADM-01.1, scope note 'new screenings only'); server/config/adminConfig.js (configDomain, domainsByGroup, registrySummary, groupedDomains, buildAdminConfigPayload); server/adminConfig.js /api/admin-config registry + /domains + /:domain + /:domain/history (admin-only, 403 otherwise; history from immutable audit_event); src/api/client.js api.adminConfig; src/pages/Settings.jsx Config Registry tab (groups, edit route, versioned flag, audited change history). test: server/tests/adminConfig.test.js (7 pass); server/tests/adminConfigApi.test.js (6 pass). Evidence: docs/evidence/W8-03/admin_config_registry.png, admin_config_domain_history.png
W8-04 | W8 Platform | Data-room folder link on the opportunity record | INTG-01 | Should | S | S7 |  | Platform squad | Folder link stored on record | Done | 2 | code: server/config/dataroomLink.js (DATAROOM_LINK_VERSION=INTG-01.1; provider vocabulary Coneshare/SharePoint/OneDrive/Google Drive/Box/Dropbox + generic fallback matched on host; https-only policy, host required, 2048 max; providerForUrl, validateDataroomLink, buildDataroomLinkRecord, describeDataroomLink); server/pipeline.js GET /dataroom-providers + GET/PUT/DELETE /opportunities/:id/dataroom-link (canViewOrg read, canWriteOrg write, 422 on invalid/http, audited dataroom_link_set / dataroom_link_cleared; pointer rides on the pipeline card as dataroom_folder); src/api/client.js pipeline.dataroomProviders/dataroomLink/setDataroomLink/clearDataroomLink; src/pages/ScreeningBoard.jsx Data-room folder panel (provider badge, Open folder, Clear, and the save editor). test: server/tests/dataroomLink.test.js (10 pass); server/tests/dataroomLinkApi.test.js (4 pass). Evidence: docs/evidence/W8-04/preparer_dataroom_link_set.png, preparer_dataroom_link_editor.png
W8-05 | W8 Platform | Bulk import of in-flight opportunities from Excel tracker with validation report | INTG-03 | Should | M | S7 |  | Platform squad | One-off import with validation report | Done | 5 | code: server/config/bulkImport.js (BULK_IMPORT_VERSION=INTG-03.1; column map for the Sirius tracker headers -> capture keys, required columns opportunity_name/owner_org_id/sector/geography/total_commitment_aed, max 500 rows, importable states draft/submission/screening; normaliseHeader, columnKeyForHeader, splitCsv/parseCsv/rowsFromMatrix, validateImportRow, buildValidationReport, importTemplateCsv); server/xlsxRead.js (dependency-free xlsx reader: shared strings, inline strings, numbers); server/bulkImport.js router /api/bulk-import (GET /policy, GET /template.csv, POST /validate dry-run report, POST /execute creates importable rows via the audited entity API + transition; admin-only via canConfigure, 403 otherwise; 422 when blocked, 400 without confirm; audits entity bulk_import action opportunities_imported); src/api/client.js api.bulkImport; src/pages/Settings.jsx Bulk Import tab (template download, validate, load, row-level report). test: server/tests/bulkImport.test.js (10 pass); server/tests/bulkImportApi.test.js (7 pass). Evidence: docs/evidence/W8-05/admin_bulk_import_report.png
W8-06 | W8 Platform | User admin hardening: deactivation immediate, all actions audited | PLT-05 | Must | S | S7 |  | Platform squad | Deactivated users lose access immediately | Done | 2 | code: server/config/userAdmin.js (USER_ADMIN_VERSION=PLT-05.1; lifecycle policy revoke_sessions_on_deactivate/ban/password_change, block_self_deactivation, deactivation_takes_effect=immediately; named audited action catalog; statuses active/deactivated/banned; userStatus/isUserActive/accessBlockReason/describeUserStatus/shouldRevokeSessions); server/users.js buildActor enforces the status at the single actor-resolution choke point (inactive or banned -> no actor; a presented session for such an account is refused, never falls through to the default identity); server/admin.js GET /api/admin/user-admin/policy, policy-driven session revocation on deactivate/ban/password/profile active-flag, POST /users/:id/reactivate, users decorated with status/status_label/can_authenticate; src/api/client.js admin.reactivateUser/userAdminPolicy; src/pages/SuperAdmin.jsx status badge + Deactivate/Reactivate swap + revoked-session reporting. test: server/tests/userAdmin.test.js (7 pass); server/tests/userAdminApi.test.js (3 pass). Evidence: docs/evidence/W8-06/admin_users_status_list.png, admin_deactivation_reactivate.png
W9-01 | W9 NFR/Release | AI governance: prompt/output logging, AI-output labelling, provider-approval evidence | NFR-03 | Must | M | S8 |  | Platform squad | Provider approved in writing before SCR-02 build | Done | 5 | server/config/aiGovernance.js owns the AI governance policy (prompt/response logging, email + secret redaction, AI-output labelling, provider approval, retention) and the provider register; server/aiGovernance.js exposes /api/ai-governance (policy + label + approval summary; admin PUT audited as entity ai_governance) plus the admin governed-call log; the LLM call path refuses an unapproved provider before the outbound call and logs a redacted, attributed row; src/components/shared/AIOutputBadge.jsx labels model output. Evidence: docs/evidence/W9-01/
W9-02 | W9 NFR/Release | Security review / vulnerability scan with no open critical/high | NFR-02 | Must | M | S8 |  | Platform squad | Scan report clean at go-live | Done | 5 | Security review and dependency advisory scan (NFR-02). server/config/securityPosture.js records the 13-control catalog and the accepted go-live scan; scripts/security_scan.mjs runs the server-runtime/production/full-tree audits, node --check over server/*.js and an injection-sink grep, exits non-zero on any open critical/high; npm audit fix cleared all critical/high (server runtime tree is 0 advisories). GET /api/ai-governance returns the posture and the AI Governance settings tab renders the gate, summary and control register. External go-live dependencies: independent pen test and UAE residency (W9-03). Evidence: docs/evidence/W9-02/
W9-03 | W9 NFR/Release | UAE data residency / hosting confirmed and signed off | NFR-01 | Must | M | S8 |  | Platform squad | Hosting design signed off by Sirius IT/security | Blocked | 5 | Data residency posture (NFR-01). server/config/residency.js classifies every dependency the running instance uses against the approved sovereign regions (me-central-1/me-central-2/uae/ae) and reports in-boundary/local/pinned/unpinned per dependency plus a posture_satisfied flag; pure classifier unit-tested in server/tests/residency.test.js (7 pass). Surfaced on GET /api/health (residency block) and in Settings -> AI Governance as a Data residency (NFR-01) panel with an unpinned / sign-off badge. BLOCKED on the external hosting sign-off, which is a Sirius IT/security activity (tracked as control uae_data_residency, status External, in W9-02) - not claimed as done here. Evidence: docs/evidence/W9-03/
W9-04 | W9 NFR/Release | Performance SIT (P95 page < 3s; screening < 15 min) | NFR-04 | Should | S | S8 |  | Platform squad | Verified with representative data | Done | 2 | Performance SIT (NFR-04). scripts/performance_sit.mjs measures P50/P95/max latency for the pipeline board, pipeline dashboard, funnel metrics, weekly reporting, portfolio register and a live screening panel, and exits non-zero when any endpoint misses the P95 budget or breaches the hard ceiling. server/config/performance.js holds the targets (P95 page budget 3000 ms, screening SLA 15 min) and the percentile/verdict helpers (unit-tested). Measured on 16,610 opportunity records: every endpoint P95 <= 44 ms, far inside the 3000 ms budget. Evidence: docs/evidence/W9-04/
W9-05 | W9 NFR/Release | Backup/restore rehearsal (RPO 24h, RTO 8h) | NFR-05 | Should | S | S8 |  | Platform squad | Restore tested once before go-live | Done | 2 | Backup/restore rehearsal (NFR-05). scripts/backup_restore_rehearsal.mjs drives a real pg_dump + scratch-database restore against the running container and reconciles the entity_record and audit_event counts; it exits non-zero on a count mismatch or an over-RTO restore. server/config/backupRestore.js holds the RPO 24h / RTO 8h gate (unit-tested). Rehearsal result: 37 MB dump, counts match exactly (16610 entity_record / 106098 audit_event), restore in ~5s vs the 8h RTO target. RUNBOOK.md documents the schedule and retention. Evidence: docs/evidence/W9-05/
W9-06 | W9 NFR/Release | Browser/device SIT (latest 2 Chrome/Edge/Safari; tablet) | NFR-06 | Should | S | S8 |  | Platform squad | Tested on listed browsers | Done | 2 | Browser/device SIT (NFR-06). scripts/browser_sit.mjs drives the Dashboard, Deal Pipeline, Screening Board and Settings journeys through real Playwright browsers at desktop and tablet profiles and fails on a render or page error. server/config/browserSupport.js holds the support matrix and gate (unit-tested). Chrome/Edge (Chromium desktop) and tablet PASS; Safari / WebKit is not installable in this environment and is recorded as an external gap, not claimed as tested. Evidence: docs/evidence/W9-06/
W9-07 | W9 NFR/Release | Usability UAT (pilot completes a submission unaided) | NFR-07 | Must | S | S8 |  | Platform squad | Pilot completes without delivery-team support | Blocked | 2 | Usability UAT (NFR-07). server/config/usability.js defines the pilot task catalog (gate tasks capture/documents/draft/sign/status), the acceptance thresholds (>=3 pilots, >=80% unaided, 0 critical issues, mean SUS >=68) and a pure scorer; server/tests/usability.test.js 8 pass. scripts/usability_uat.mjs scores recorded pilot sessions and exits non-zero when they miss the gate. BLOCKED: no pilot session recorded yet (pilot unavailable in this environment) - the harness reports the gate PENDING rather than claiming a pass. Run sheet + session template: docs/evidence/W9-07/.
W9-08 | W9 NFR/Release | Existing systems review written up (integration points agreed) | INTG-02 | Must | S | S8 |  | Delivery | Findings documented; points agreed pre-build | Blocked | 2 | Existing systems review (INTG-02). docs/Existing_Systems_Review.md inventories every external system the MVP actually calls, read from the code: Postgres (DATABASE_URL), object storage (S3_ENDPOINT/S3_REGION), AI model (OPENAI_BASE_URL), email (Resend via NOTIFY_BASE_URL), SMS gateway (no provider - open), data room (CONESHARE_*), antivirus scanner (DOCUMENT_SCAN_COMMAND, builtin EICAR + optional external engine), and SSO (Better Auth OIDC/SAML, provider open). Five open items listed for the Sirius discovery workshop. BLOCKED: the write-up is done but the points must be AGREED in a Sirius IT workshop (external); no agreement is claimed. Evidence: docs/evidence/W9-08/ + docs/Existing_Systems_Review.md.
W1-11 | W10 Sample data | Clean all sample / demo data: remove demo opportunities, orgs, users and uploaded document bytes; keep only structured MVP fixtures seeded on demand | PLT-01, INT-01 | Must | S | S1 | W1-03 | Intake squad | Running with SEED_DEMO_DATA=false leaves zero demo rows; cleanup removes prior demo artifacts idempotently and is safe to re-run | Done | 3 | docs/evidence/W1-11/ - admin_sample_data_console.png (seed profile + clean/load controls), admin_seed_audit_trail.png (seeded audit events). Harness: scripts/capture_evidence.mjs. Test: server/tests/seedCleanup.test.js (5 pass), seedProfiles.test.js (7 pass). Commit 57cda82
W1-12 | W10 Sample data | MVP sample mapping: structured, deterministic fixtures (org tree, users + roles, portfolio register, one fully-worked opportunity per persona journey, a theme-aligned case and an outside-appetite case) derived from Sirius subsidiary data and the nature-of-business map | PLT-01, ENT-04, INT-01, SCR-02 | Must | M | S1 | W1-11 | Intake squad | Every MVP persona journey has deterministic seed rows; the mapping is documented in docs/sample-data/MVP_Sample_Data_Map.md and loads from a single seed command | Done | 5 | docs/evidence/W1-12/ - admin_sample_inventory.png, preparer_intake_fixtures.png, analyst_screening_fixtures.png, preparer_fixture_state_refinement.png. 10 fixtures / 19 docs / 12 transitions; states draft 4, screening 4, submission 1, refinement 1. Harness: scripts/capture_evidence.mjs. Commit e5eda59
W1-13 | W10 Sample data | Screenshot-evidence validation: capture per-TODO evidence (persona, feature covered, screenshot, how it works) into the structured path and only mark a TODO Done when its evidence exists | NFR-07 | Must | M | S1 | W1-12 | Intake squad | Every Done TODO carries a screenshot at docs/evidence/<TODO-ID>/<persona>_<feature>.png; rows without evidence stay In progress | Done | 5 | docs/evidence/W1-13/ - admin_evidence_index.png (contact sheet generated from docs/evidence/). Convention: docs/evidence/README.md. Harness: scripts/capture_evidence.mjs + scripts/generate_evidence_index.mjs. Rule enforced: W1-11/W1-12 promoted to Done only once their shots existed; W1-03/W1-04 still In progress pending shots

## Slices
Slice | Weeks | Outcome | Scope | Exit criteria
S0 | W0 | Reconcile & freeze | BRD-to-plan reconciliation signed; backlog of record approved | Plan signed; scope (62 Must + 20 Should) frozen
S1 | W1-W3 | Intake governance | Self-screen, below-floor exception, 6-section form, 10-gate checklist, accretion, greenfield, CEO/CFO attestation, withdraw, duplicate warning | INT-02/03/06/07/08/09/10/13 pass; J1/J2/J3 green
S2 | W3-W6 | Financials & returns | Financial summary, 3-statement check, 3-scenario returns, hurdle table, WACC, sources/uses, budget, valuation/exit, cross-border, FX | FIN-01..FIN-10 pass
S3 | W5-W8 | Screening & scorecard | Screening panel, hard/soft filters, disqualifiers, weighted scorecard + config, quality score, two-lens floor, proposed scores, conflict/synergy, sanctions field, alignment citation | SCR-01..SCR-09, SCO-01..SCO-05 pass
S4 | W6-W8 | Entity, docs & templates | Portfolio register, strategy indexing, versioned profile/mandate, type-driven checklist, versioned uploads + scan, sufficiency check, data-point mapping, templates | ENT-01..04, DOC-01..06 pass
S5 | W8-W10 | Governance & audit hardening | Reason codes, DoA, related-party overlay, internal/shared comments, hash-chained audit, presentation scheduling, notification frequency | WF-05/06/07/08, AUD-01/03, NTF-01 pass; J7 green
S6 | W9-W11 | Reporting & output | IHC weekly report, pipeline filters, funnel/cycle metrics, 6-page pack export, QR verification | DSH-01/03/04, OUT-02/03 pass
S7 | W10-W12 | Platform, auth & config | SSO/MFA, i18n completion, unified admin config, data-room link, bulk import, user-admin hardening | PLT-04/05/06, ADM-01, INTG-01/03 pass
S8 | W12-W13 | Hardening & NFR | AI governance, security scan, residency, performance, backup, browser SIT, usability | NFR-01..NFR-07 pass
S9 | W13-W14 | UAT & sign-off | Full-persona UAT on expanded scope; defect triage | DoD met; Sirius signs off
S10 | W14-W15 | Pilot rollout | Pilot subsidiary live; first cluster onboarded | Pilot submitting in-portal

## Open Decisions
# | Type | Item | Owner | Status
Q1 | Decision | Identity provider for PLT-04 (Entra ID?) and whether subsidiaries share the tenant | Sirius | Open
Q2 | Decision | Confirm scorecard weight set and score bands (SCO-01/02/05) | Sirius | Open
Q3 | Decision | Confirm hurdle placeholders: WACC margin, greenfield IRR, concentration, leverage (FIN-04) | Sirius | Open
Q4 | Decision | Confirm SLA per state (WF-02) | Sirius | Open
Q5 | Decision | Provide the current Friday tracker template (DSH-03) | Sirius | Open
Q6 | Decision | Provide templates + manual Excel process (DOC-06) and in-flight tracker (INTG-03) | Sirius | Open
Q7 | Decision | Existing sanctions/PEP screening provider, if any (SCR-08) | Sirius | Open
Q8 | Decision | Standard three-statement model template mandated? (FIN-02) | Sirius | Open
R1 | Risk | W2 financial scope is large and gates W3/W7; slipping W2 slips the release | Eng | Tracking
R2 | Risk | PLT-04 SSO depends on external IdP access; long lead time | Eng/Sirius | Tracking
R3 | Risk | Scope wider than the existing Screening MVP plan; needs a written change note | Sirius PO | Tracking